## GANTT Master
| 0-10 Activities |  |  | Input Form for Site Supervisors: (to update th status on Daily Basis)
Get Client 10% & Approval to start design work
| 10-50 Activities |  |  | Status | Revised Date
| Finalize Designs |  |  | Yet to Start
| Finalize BOQ |  |  | In Progress
| Select Vendors based on quotes, timelines, quality |  |  | Completed
50-100 Activities
Receive 50% advance from Client
Place Vendor POs & release advance payment
Select all Materials
Select all Appliances
Select Others
50-100 Project Management System
| Services | Dependency | Start Date | End Date | # of Days | % Completion | Status | Revised Date
1 | Site Startup Work | [5 empty] | Yet to Start
| Inspection of site, document all issues | [5 empty] | In Progress
| Approvals from Authorities & Insurance | [5 empty] | Completed
Floor Covering
Site Marking
Site Pics of all space shared with client
2 | Civil Work
Demolition
Debris Disposal & Transportation
Construction
Tiling
Waterproofing
3 | Plumbing Work
4 | Electrical Work
Conduits, Jari, Wiring Work
MDB Installation
WiFi, Booster, Exhaust Point, CCTV Installation
Gala Cutting
Lights Fixing
Installation & Testing of Switchboards
5 | HVAC Work
Piping & Ducting work
AC Grill Cutting & Fixing
Installing out door units
Fixing & Testing AC Units
6 | Automation Work | Electrical
Wiring Work
Installing Panels
ADB Installation
Programming & Testing
7 | Pest Control
1st Round
2nd Round
8 | False Ceiling
Framing
Gypsum Board
Finalisation
Bathrooms False Ceiling
9 | Window Pelmets Carpentry
Marking, Ply cutting
Pelmet Installation
10 | Quality Check Phase 1
10 | Painting
Leveling, Lambi, Primer
1st Coat
Final Coat
11 | Polishing | Carpentry
Scraping, Preparing
Polishing Final Coat
PU Final Coat
12 | Kitchen - Modular
Drawings with Materials & Specifications
Site Marking & Measurements
Final Drawings Signed & Sent for Production
Delivery & Installation of Counter Top
Quality Check at Factory
Delivery of Kitchen
Installation of Kitchen
Shutters- if from separate vendor
13 | Wardrobes-Modular
Drawings with Materials & Specifications
Site Marking & Measurements
Final Drawings Signed & Sent for Production
Quality Check at Factory
Delivery of Wardrobes
Installation of Wardrobes
Shutters- if from separate vendor
14 | Carpentry
Fixed Paneling Work
Fixed Furniture Units
Wooden Flooring
Quality Check & Measurments Check
15 | Modular Furniture
Drawings with Materials & Specifications
Site Marking & Measurements
Final Drawings Signed & Sent for Production
Quality Check at Factory
Delivery of Modular Furniture
Installation of Furniture
15 | Custom Loose Furniture
Drawings with Materials & Specifications
Site Marking & Measurements
Final Drawings Signed & Sent for Production
Quality Check at Factory, Delivery
Installation of Loose Furniture
16 | Quality Check Phase 2
16 | Sourced Loose Furniture
17 | Curtains
Final Fabric Selection
| Delivery & Installation | Painting, Polishing
18 | WallPaper
Final WallPaper Selection
| Delivery & Installation | Painting, Polishing
19 | Client Payments
50% Received
75% Received
90% Received
100% Received
20 | Materials Selections
Tiles
Laminate
Veneer
T-Strips Inlay
Glass
Mirror
Marble/Onyx/Quartz
Upholstery Fabrics
Curtain Fabrics
Curtain Rods
WallPaper
Lights- Fixed
Lights-Decorative
Fans
Exhaust Fans
Electrical Switchboards
Wooden Flooring
Bathroom Fittings
Cushion Seating on Shoe rack small unit
Mattresses
21 | Appliances Selection
Kitchen Exhaust Fan(s)
Curtain Motors
Chimney
Hob
Oven
Microwave
Dishwasher
Washing Machine
Coffee Machine
Kitchen Fridge
Bar Fridge
Air Conditioners
Water Purifiers
Water Softeners
AV Sound System
22 | Others
Grills/Railings
Pigeon/Birds Nets
Mobile Booster
Fire Sprinklers
23 | Décor, Carpets, Art Selections
24 | Floor Polishing
25 | Deep Cleaning & Handover
26 | Weekly Progress Report Sent
Week 1
Week 2
| Client Details (to be filled by OPS Team) | from master | from master | from master | Y/N | Y/N | Y/N | Y/N | Y/N | Y/N | Y/N | Y/N
| Client Name | Project Name | Typology | Location | EL Signed | BOQ Approved | Design Fees | Drawings Signed | POs Issued | PIs Issued | Tax Invoice Issued | Warranty Card Issued
| Mr ABC | Ahuja Infinity | 3bhk | Mumbai
Dashboard
| Client Name | Stage | Start Date | End Date | Status
+ | Mr ABC | 50-100 |  |  | On Track
+ | Mr XYZ | 50-100 |  |  | Delayed
+ | Use '+ to see full details as above