## GANTT Master
| 0-10 Activities |  |  | Input Form for Site Supervisors: (to update the status on Daily Basis)
Get Client 10% & Approval to start design work
| 10-50 Activities |  |  | Status | Revised Date
| Finalize Designs |  |  | Yet to Start
| Finalize BOQ |  |  | In Progress
| Select Vendors based on quotes, timelines, quality |  |  | On Hold
| 50-100 Activities |  |  | Completed
Receive 50% advance from Client
Place Vendor POs & release advance payment
| Select all Materials | Flow
| Select all Appliances | Create Project
| Select Loose Furniture | Update Planner
| Select Others | Add Sub Activites/Tasks=MakeList |  |  | The Subactivities can pull from the BOQ
|  | GANTT |  |  | Hence each BOQ item will be tagged with a Service Code from 1-26
50-100 Project Management System
| Services (Master) | Dependency | Start Date | End Date | # of Days | % Completion as per original end date | % Completion as per Revised end date | Status | Revised Start Date | Revised Completion Date
1 | Site Startup Work |  | x | y | 25 | 80% |  | Yet to Start
| Inspection of site, document all issues | [5 empty] | In Progress
| Approvals from Authorities | [5 empty] | Completed
Floor Covering
Site Marking
2 | Civil Work
Demolition
Construction
Tiling
Waterproofing
3 | Plumbing Work
4 | Electrical Work
Conduits, Jari, Wiring Work
MDB Installation
Gala Cutting
Lights Fixing
Installation & Testing of Switchboards
5 | HVAC Work
Piping & Ducting work
Installing out door units
Fixing & Testing AC Units
6 | Automation Work | Electrical
Wiring Work
Installing Panels
ADB Installation
Programming & Testing
7 | Pest Control
1st Round
2nd Round
8 | False Ceiling
Framing, Gypsum
Bathrooms False Ceiling
9 | Painting
Leveling, Lambi, Primer
1st Coat
Final Coat
10 | Polishing | Carpentry
Scraping, Preparing
Polishing Final Coat
PU Final Coat
11 | Kitchen - Modular
Drawings with Materials & Specifications
Site Marking & Measurements
Final Drawings Signed & Sent for Production
Selection of Accessories
Delivery & Installation of Counter Top
Installation of Kitchen
Shutters- if from separate vendor
12 | Wardrobes-Modular
Drawings with Materials & Specifications
Site Marking & Measurements
Final Drawings Signed & Sent for Production
Selection of Accessories
Installation of Wardrobes
Shutters- if from separate vendor
13 | Carpentry
Fixed Paneling Work
Fixed Furniture Units
14 | Modular Furniture
Drawings with Materials & Specifications
Site Marking & Measurements
Final Drawings Signed & Sent for Production
Installation of Furniture
15 | Custom Loose Furniture
Drawings with Materials & Specifications
Site Marking & Measurements
Final Drawings Signed & Sent for Production
Installation of Loose Furniture
16 | Sourced Loose Furniture
Final Loose Furniture Selection
Delivery & Installation of Loose Furniture
17 | Curtains
Final Fabric Selection
| Delivery & Installation | Painting, Polishing
18 | WallPaper
Final WallPaper Selection
| Delivery & Installation | Painting, Polishing
19 | Client Payments
50% Received
75% Received
90% Received
100% Received
20 | Materials Selections
Tiles
Laminates
Veneer
Glass
Glass Films
Mirror
Marble/Onyx
T-Strips /Inlays
Wall Textures
Upholstery Fabrics
Curtain Fabrics
Curtain Rods
WallPaper
Lights- Fixed
Lights-Decorative
Fans
Exhaust Fans
Electrical Switchboards
Wooden Flooring
Bathroom Fittings
Mattresses
Door Handles & Locks
21 | Appliances Selection
Kitchen Exhaust Fan(s)
Curtain Motors
Chimney
Hob
Oven
Microwave
Dishwasher
Washing Machine
Coffee Machine
Kitchen Fridge
Bar Fridge
Air Conditioners
Geysers/Water Heaters
Water Purifiers
Water Softeners
Garbage Disposal
AV Sound System
22 | Others
Grills/Railings
Pigeon/Birds Nets
Window/Door Screens
Drying Racks
Mobile Booster
Fire Sprinklers
Hardware like Sliding Fittings (if applicable)
23 | Décor, Carpets, Art Selections
24 | Floor Polishing
25 | Deep Cleaning & Handover
26 | Weekly Progress Report Sent
Week 1
Week 2
| Client Details (to be filled by OPS Team & Checked by Accounts Team) | from master | from master | from master | Y/N | Y/N | Y/N | Y/N | Y/N | Y/N | Y/N | Y/N | Amount | Amount
| Client Name | Project Name | Typology | Location | EL Signed | BOQ Approved | Design Fees | Drawings Signed | POs Issued | PIs Issued | Tax Invoice Issued | Warranty Card Issued | Next Payment Due | Total Outstanding
| Mr ABC | Ahuja Infinity | 3bhk | Mumbai
Dashboard
| Client Name | Stage | Start Date | End Date | Status
+ | Mr ABC | 50-100 |  |  | On Track
+ | Mr XYZ | 50-100 |  |  | Delayed
+ | Use '+ to see full details as above